## Timeline
May |  | Complete end to end workable demo | John | Yang | Time | Status
Target | 1 | User requirement | Yes | Review | 2022-05-06
| 2 | Front end user login | Yes | Review | 2022-05-06
| 3 | Front end save model, result, setting state, data | Yes | Review | 2022-05-13
| 4 | Front end load model, result, setting state, data | Yes | Review | 2022-05-13
| 5 | Class structure planning | Review | Yes | 2022-05-06
| 6 | Class - loader | As needed | Yes | 2022-05-13
| 7 | Class - modeller (Logistic, Simple) | As needed | Yes | 2022-05-20
| 8 | Class - outputer (output table, model pickle, setting table) | As needed | Yes | 2022-05-27
| 9 | Class - Streamlit (visual) | Yes | Yes | June
| 10 | Class - modeller (Boosting, more complex) | Yes | Yes | June
| 11 | Wix - Front end | Yes | Review | July

## User Requirement
Function | Priority | User requirement | Solution
Data loader | High | I want to download a copy of data template
Data loader | High | I am able to input company specific factors
Data loader | High | I want to download a copy of instruction
Data loader | High | I want to upload data via an excel file
Data loader | Mid | I want to choose which factors to run/not run
User Management | High | I want to login with email and password
User Management | High | I want to change my password after login
Storage | Mid | I want to view saved run with name and time sort by latest first
Storage | Mid | I want to load a saved run including data, setting, and result
Storage | Mid | I want to save a run including data, setting, and result with a name
Data validation | High | I want to download a copy of invalid data to correct
Data validation | High | I want to see which record is invalid and the reason
Setting | Low | I want to select what factors to include in the analysis
Setting | Low | I want to select the monotonic constrain for each factor in the analysis (up, down, or no constrain)
Output | High | I want to see how many record is submitted
Output | High | I want to see how many record is successful run
Output | High | I want to see how many record is invalid
Output | High | I want to see num of voluntary turnover
Output | High | I want to see rate of voluntary turnover
Output | High | I want to see my top 5 drivers of turnover
Output | High | I want to see my top 5 drivers of turnover and how each impact the turnover rate
Output | Mid | I want to see how does change in each of my drivers impact the turnover risk
Output | Low | I want to download the importance of my drivers and the impact in an excel file
Output | High | I want to adjust one/many factors to see how it impact my overall turnover rate as a company
Output | Low | I want to see each employee's turnover risk (prob of turnover)
Output | Low | I want to see an risk indicator of each employee's turnover risk (high, mid ,low)